## Sheet1
Week | Goal # | Description | Fuctionality | Status
1 | 1 | Add Auto Filling Features the Driver Print Out Form | Client clicks on event from calendar, resulting driver form displays event information | Completed
| 2 | Calendar Event Population | Client views calendar, calendar shows all reservations stored in reservation table, on the date of the reservation | Completed
| 3 | Rework Forms to better suit customer | Client is provided needed fields, such as pick up address previously not included | Completed
2 | 1 | Implement Reservation Saving abilities | Client inserts information in the Reservation form, after clicking submit the a new reservation with the correct information is added to the table | Completed
| 2 | Rework Forms to better suit customer | Client is provided needed fields, previously not included | Completed
3 | 1 | Update Client | Latest material sent to customer for review | Completed
| 2 | Implement Car Availability Features | Client can easily tell when a particular car is in use and when it is available | Completed
4 | 1 | Code Freeze | Freeze code changes to focus on review | Completed
| 2 | Documentation | Document Progress and Plan for next Cycle | Completed